## QA Testing Report
Column1
website:- https://www.khajina.com/
Tested by:- Rushikesh Shinde
Date: 13--05-2026
Defect ID | Module | Test Case | Defect Description | Expected Result | Actual Result | Priority | Tested On | Remarks | Status
Defect -001 | Home Page | Name is cropped | Text/content name appears cropped on the page. | Full name should display properly. | Name is partially cropped. | High | Web |  | Fixed
Defect -002 | Home Page | Page loading issue | Page loading is slow or unstable. | Page should load smoothly. | Loading delay observed. | High | Web |  | not fixed
Defect -003 | Category Page | Duplicate category names | Duplicate category names may confuse users. | Unique category names should appear once. | Duplicate categories displayed. | Medium | Web | TODDLER FAVOURITE / TODDLER'S FAVOURITE | Fixed
Defect -004 | Category Page | Duplicate category names | Duplicate category names may confuse users. | Unique category names should appear once. | Duplicate categories displayed. | Medium | Web | CHH. SHIVAJI MAHARAJ / CHHATRAPATI SHIVAJI MAHARAJ | Fixed
Defect -005 | Category Page | Duplicate category names | Duplicate bilingual category names displayed. | Only one consistent category should display. | SCIENCE / विज्ञान / Science duplicated. | Medium | Web |  | Fixed
Defect -006 | Category Page | Duplicate category names | Poems category duplicated in multiple formats. | Only one standardized category name should display. | Duplicate category names displayed. | Medium | Web |  | Fixed
Defect -007 | shop Page | Unnecessary blank space | Extra whitespace appears between sections. | Spacing should be consistent. | Large blank space visible. | Medium | Web
Defect -008 | Shop Page | Search bar redirect issue | Clicking search redirects to shop page instead of allowing typing. | User should type directly into search bar. | Redirect occurs on click. | High | Web |  | Fixed
Defect -009 | Home Page | Missing navigation option | Home navigation disappears during loading. | Navigation should remain visible. | Navigation option missing temporarily. | Medium | Web |  | Fixed
Defect -010 | Category Page | Subcategory deletion issue | Deleted subcategory still appears. | Subcategory should be removed completely. | Subcategory remains visible. | High | Web |  | not fixed
Defect -011 | Product Page | Product images not loading | Product images fail to render. | Images should load properly. | Broken/missing images displayed. | High | Web
Defect -012 | Shop Page | Gift dropdown clicked on gift card page loading issue | Gift Sets page loads unexpectedly from Gifts dropdown. | Dropdown should show proper categories. | gift set page loading . | Medium | Web
Defect -013 | Authors Page | Alignment issue | UI alignment is inconsistent. | Elements should align properly. | Misalignment observed. | Medium | Web |  | Fixed
Defect -014 | Category Page | Blue icon before loading | Unwanted blue icon appears before page loads. | No unnecessary icon should display. | Blue icon flashes before loading. | Low | Web |  | Fixed
Defect -015 | Category Page | Language filter redirect issue | English/Marathi buttons redirect to shop page. | Categories should filter on same page. | Redirect occurs instead of filtering. | High | Web
Defect -016 | Category Page | Upper box cropped | Upper box slightly cropped. | Container should display fully. | Top portion cropped. | Medium | Web
Defect -017 | Category Page | Image mismatch and spelling issue | Images and spellings are incorrect. | Correct image and spelling should display. | Mismatch observed. | Medium | Web
Defect -019 | Contact Page | Unexpected popup/window | Unexpected window appears in contact section. | No unwanted popup should appear. | Popup displayed unexpectedly. | Medium | Mobile |  | Fixed
Defect -020 | Home Page | Button not clickable | Button is unresponsive in mobile view. | Button should work properly. | Button cannot be clicked. | High | Mobile |  | Fixed
Defect -021 | shop Page | Buttons merged | Buttons overlap/merge together. | Buttons should have proper spacing. | Buttons merged visually. | Medium | Mobile |  | Fixed
Defect -022 | Author Section | Author name formatting inconsistency | Author names use inconsistent formatting. | Names should follow standard format. | Mixed uppercase and Marathi text. | Low | Web
Defect -023 | Blog Page | Read More clicked on | Read More opens 404 page. | Correct blog details page should open. | Page Not Found displayed. | High | Web |  | Fixed
Defect -024 | Category Page | Popular categories alignment issue | Popular categories alignment is improper. | Cards should align consistently. | Misalignment visible. | Medium | Web |  | Fixed
Defect -025 | Shop Page | Books not found | Books missing in categories except Story Books. | Books should display in all categories. | Books not found. | High | Web | Activity, Science, Marathi, English, Gift Sets | Fixed
Defect -026 | iOS Safari Testing | Blank container issue | Blank container visible in contact section. | No unnecessary blank container. | Whitespace displayed. | Medium | iOS Safari
Defect -027 | iOS Safari Testing | Navbar overlap issue | Header/navbar overlaps hero section. | Proper responsive spacing required. | Overlap observed. | High | iOS Safari |  | Fixed
Defect -028 | iOS Safari Testing | Author images broken | Author images not rendering properly. | Images should load correctly. | Broken placeholders visible. | High | iOS Safari |  | Fixed
Defect -029 | iOS Safari Testing | Author text overflow | Author names overflow/truncate. | Text should wrap properly. | Overflow issue visible. | Medium | iOS Safari |  | Fixed
Defect -030 | iOS Safari Testing | Excessive blank spacing | Large blank space before Ready to Get Started card. | Consistent spacing required. | Excessive spacing visible. | Medium | iOS Safari
Defect -031 | iOS Safari Testing | Product card alignment issue | Product cards have uneven bottom alignment. | Cards should align uniformly. | Inconsistent layout observed. | Medium | iOS Safari
Defect -032 | iOS Safari Testing | Add to Cart alignment issue | CTA buttons are misaligned. | Buttons should align consistently. | Uneven button placement. | Medium | iOS Safari
Defect -033 | iOS Safari Testing | Quantity selector alignment issue | Quantity selector spacing/alignment issue. | Controls should be centered. | Alignment issue observed. | Medium | iOS Safari
Defect -034 | Navigation Bar | Navigation Bar Items Missing on Galaxy Tab S4 | Some sections from the navigation bar are not visible on the Galaxy Tab S4 tablet. | All navigation bar items including Cart should be visible properly. | Some navigation items are hidden and Cart option is missing. | High | Galaxy Tab S4 Tablet
Defect -035 | Product Section | Add to Cart and Wishlist Button Alignment Issue | There is unnecessary space between the price and Add to Cart button. Add to Cart and Wishlist buttons are not properly aligned inside the book container. | Buttons should be properly aligned with proper spacing. | Buttons appear misaligned with unnecessary spacing. | Medium | Tablet View
Defect -036 | Checkout Page | Extra Space Between Order Summary and Shipping Section | There is unnecessary space between the Order Summary and Shipping sections. | Sections should have proper consistent spacing. | Large unnecessary gap exists between sections. | Medium | Tablet View
Defect -037 | My Orders | Extra Space Between Order ID and Item Ordered Section | There is unnecessary space between Order ID and Item Ordered sections in My Order tab. | Proper spacing should be maintained between sections. | Large blank space appears between sections. | Medium | Tablet View
Defect -038 | Checkout Section | Multiple Unnecessary Spaces in Checkout Section | Multiple unnecessary spaces are visible in the Checkout section. | Checkout layout should maintain proper spacing consistency. | Multiple unwanted spaces disturb the UI layout. | Medium | Tablet View
Defect -039 | Navigation Section | Navigation Section Overlapping | Navigation section overlaps in iPad Pro view. | Navigation section should display properly without overlapping. | Navigation elements overlap each other. | High | iPad Pro
Defect -040 | Product Section | Add to Cart and Wishlist Button Overlapping | Add to Cart and Wishlist buttons overlap in iPad Pro view. | Buttons should display separately with proper alignment. | Buttons overlap each other causing UI issue. | High | iPad Pro
Defect -041 | Categories Page | Language Filter Redirection Issue | When you click "English" or "Marathi" buttons on the /categories page — instead of filtering categories by language on the same page, it redirects you to the /shop page. | Categories should be filtered by selected language on the same /categories page. | User is redirected to the /shop page after clicking the language buttons. | Medium | web |  | not fixed
Defect -042 | FAQ Page / View Cart Page | Gift Wrapping Price Mismatch | The gift wrapping price is different on the FAQ page and View Cart page. | Gift wrapping price should be the same on both FAQ and View Cart pages. | Different gift wrapping prices are displayed on the FAQ page and View Cart page. | Medium | Web |  | Fixed