## UAT Checklist
Sr No | Module | Section | Test Case ID | Checkpoint | Steps | Expected Result | Priority | Rushikesh | Aditi | Siddhi | Chinmay | Tanishq | Overall Status | Remarks / Defect ID
1 | Authentication & Session | Login | 1.1.1 | Valid login with OTP | Enter valid username + password + OTP → Submit | Session created, redirect to dashboard, LoginLog recorded | Critical | ☑ | ☐ | ☑ | ☐ | ☐ | In Progress
2 | Authentication & Session | Login | 1.1.2 | Wrong password | Enter valid username + wrong password → Submit | "Invalid credentials" error, failedLoginAttempts incremented | Critical | ☑ | ☐ | ☑ | ☐ | ☐ | In Progress
3 | Authentication & Session | Login | 1.1.3 | Wrong OTP | Enter valid creds + wrong OTP → Submit | "Invalid OTP" error | Critical | ☑ | ☐ | ☑ | ☐ | ☐ | In Progress
4 | Authentication & Session | Login | 1.1.4 | Account lockout after 5 attempts | Enter wrong password 5 times | Account locked for 15 min, "Account locked" message | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I entered 5 times wrong password but Accountant is not locked
5 | Authentication & Session | Login | 1.1.5 | Login while locked | Wait < 15 min, enter correct creds | "Account locked" even with correct creds | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Account wasn’t locked, so I didn’t check
6 | Authentication & Session | Login | 1.1.6 | Login after lockout expires | Wait > 15 min, enter correct creds | Login succeeds, failedLoginAttempts reset | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Account wasn’t locked, so I didn’t check
7 | Authentication & Session | Login | 1.1.7 | Expired password (90 days) | Login with creds where passwordChangedAt > 90 days | Login succeeds but mustChangePassword=true, redirect to /account/security | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
8 | Authentication & Session | Login | 1.1.8 | Inactive user login | Deactivate user, attempt login | Login rejected | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I didn’t check it because deactivation was not working
9 | Authentication & Session | Login | 1.1.9 | Empty username | Submit with blank username | Validation error | Medium | ☑ | ☐ | ☑ | ☐ | ☐ | In Progress
10 | Authentication & Session | Login | 1.1.10 | Empty password | Submit with blank password | Validation error | Medium | ☑ | ☐ | ☑ | ☐ | ☐ | In Progress
11 | Authentication & Session | Login | 1.1.11 | Late login detection | Login after work start time + grace minutes (non-admin) | LoginLog recorded with isLate=true | High | ☑ | ☐ | ☑ | ☐ | ☐ | In Progress
12 | Authentication & Session | Login | 1.1.12 | On-time login | Login before work start time + grace (non-admin) | LoginLog with isLate=false | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
13 | Authentication & Session | Login | 1.1.13 | Admin login is never late | Admin logs in after start time | LoginLog with isLate=false (admins exempt) | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
14 | Authentication & Session | Logout | 1.2.1 | Normal logout | Click logout | Session destroyed, LoginLog updated with logoutAt | High | ☐ | ☐ | ☑ | ☐ | ☐ | In Progress
15 | Authentication & Session | Logout | 1.2.2 | Record-logout API | POST /api/auth/record-logout | logoutAt timestamp updated on latest LoginLog | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
16 | Authentication & Session | Password Reset | 1.3.1 | Request password reset | Go to /forgot, enter valid email/username | Reset email sent, PasswordResetToken created | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
17 | Authentication & Session | Password Reset | 1.3.2 | Invalid identifier | Enter non-existent email | Vague success message (no user enumeration) | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
18 | Authentication & Session | Password Reset | 1.3.3 | Complete reset with valid token | Follow reset link, enter new password | Password updated, token consumed | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
19 | Authentication & Session | Password Reset | 1.3.4 | Expired/invalid token | Use expired or tampered token | Error message | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
20 | Authentication & Session | Password Reset | 1.3.5 | Password mismatch | New password ≠ confirm password | Validation error | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
21 | Authentication & Session | Session Management | 1.4.1 | Session idle timeout | Leave session idle beyond configured timeout | Redirect to login | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
22 | Authentication & Session | Session Management | 1.4.2 | Forced password change blocks navigation | User with mustChangePassword=true tries to navigate away from /account/security | Redirected back to /account/security | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
23 | User Management | Create User (saveUser) | 2.1.1 | Create user with all fields | Fill fullName, email, username, role, phone, employeeCode, parentId, joiningDate, password | User created, audit logged, revalidate /users | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
24 | User Management | Create User (saveUser) | 2.1.2 | Missing full name | Omit fullName | Error: "Full name is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
25 | User Management | Create User (saveUser) | 2.1.3 | Missing email | Omit email | Error: "Email is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
26 | User Management | Create User (saveUser) | 2.1.4 | Missing username | Omit username | Error: "Username is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
27 | User Management | Create User (saveUser) | 2.1.5 | Invalid role | Set role to "SUPERADMIN" | Error: "Select a valid role." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please select an item in the list" this error msg will be generate
28 | User Management | Create User (saveUser) | 2.1.6 | Missing password on create | Omit password for new user | Error: "Password is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
29 | User Management | Create User (saveUser) | 2.1.7 | Duplicate email | Use email already in database | Prisma unique constraint error | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
30 | User Management | Create User (saveUser) | 2.1.8 | Duplicate username | Use username already in database | Prisma unique constraint error | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
31 | User Management | Create User (saveUser) | 2.1.9 | Create with each valid role | Test ADMIN, MANAGER, TEAM_LEADER, RECRUITER, ACCOUNTANT | Each role accepted | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
32 | User Management | Create User (saveUser) | 2.1.10 | Optional fields omitted | Create with only required fields | User created with null optional fields | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
33 | User Management | Update User (saveUser with userId) | 2.2.1 | Update name and role | Set userId + new fullName + new role | User updated, audit logs before/after | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
34 | User Management | Update User (saveUser with userId) | 2.2.2 | Update password | Set new password on existing user | hashedPassword updated, passwordChangedAt reset, failedLoginAttempts=0, lockedUntil=null | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
35 | User Management | Update User (saveUser with userId) | 2.2.3 | Update without password | Omit password field on existing user | Password unchanged | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
36 | User Management | Update User (saveUser with userId) | 2.2.4 | Non-existent userId | Set userId to invalid ID | Prisma error (record not found) | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
37 | User Management | Toggle User (toggleUser) | 2.3.1 | Deactivate user | toggleUser(userId, false) | isActive=false, audit logged | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | users:1 Failed to load resource: the server responded with a status of 500 ()
38 | User Management | Toggle User (toggleUser) | 2.3.2 | Reactivate user | toggleUser(userId, true) | isActive=true, audit logged | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
39 | User Management | Toggle User (toggleUser) | 2.3.3 | Toggle non-existent user | Pass invalid userId | Error: "User not found." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
40 | User Management | Employee Schedule (saveEmployeeSchedule) | 2.4.1 | Create schedule | Set userId, startTime, endTime, day_1..day_5, graceMinutes | EmployeeSchedule created via upsert, audit logged | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
41 | User Management | Employee Schedule (saveEmployeeSchedule) | 2.4.2 | Update existing schedule | Change times on user with existing schedule | Schedule updated (upsert) | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
42 | User Management | Employee Schedule (saveEmployeeSchedule) | 2.4.3 | Missing user | Omit userId | Error: "User is required." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
43 | User Management | Employee Schedule (saveEmployeeSchedule) | 2.4.4 | Missing start time | Omit workStartTime | Error: "Start and end time are required." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
44 | User Management | Employee Schedule (saveEmployeeSchedule) | 2.4.5 | No working days selected | Omit all day_1 through day_7 | Error: "Select at least one working day." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
45 | User Management | Employee Schedule (saveEmployeeSchedule) | 2.4.6 | Remove schedule | removeEmployeeSchedule with valid userId | Schedule deleted, fallback to global | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | the schedule is not getting added, I can't check why it's not getting removed yet
46 | User Management | Employee Schedule (saveEmployeeSchedule) | 2.4.7 | Remove non-existent schedule | Remove for user without custom schedule | Success: "Already using global defaults." | Low | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | the schedule is not getting added, I can't check why it's not getting removed yet
47 | RBAC & Permissions |  | 3.1 | ADMIN has all permissions | Check can("ADMIN", perm) for every permission | All return true | Critical | ☑ | ☐ | ☑ | ☐ | ☐ | In Progress
48 | RBAC & Permissions |  | 3.2 | RECRUITER cannot manage users | can("RECRUITER", "users:manage") | Returns false/undefined | Critical | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
49 | RBAC & Permissions |  | 3.3 | RECRUITER can create candidates | can("RECRUITER", "candidates:create") | Returns true | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
50 | RBAC & Permissions |  | 3.4 | ACCOUNTANT has billing:full | can("ACCOUNTANT", "billing:full") | Returns true | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
51 | RBAC & Permissions |  | 3.5 | ACCOUNTANT cannot manage attendance | can("ACCOUNTANT", "attendance:manage") | Returns false | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
52 | RBAC & Permissions |  | 3.6 | MANAGER cannot manage billing | can("MANAGER", "billing:full") | Returns false | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
53 | RBAC & Permissions |  | 3.7 | TEAM_LEADER can assign jobs | can("TEAM_LEADER", "jobs:assign") | Returns true | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
54 | RBAC & Permissions |  | 3.8 | TEAM_LEADER cannot create jobs | can("TEAM_LEADER", "jobs:full") | Returns false | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
55 | RBAC & Permissions |  | 3.9 | Invalid role string | isPortalRole("SUPERADMIN") | Returns false | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
56 | RBAC & Permissions |  | 3.10 | Undefined role | isPortalRole(undefined) | Returns false | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
57 | RBAC & Permissions | Permission Enforcement on Server Actions | 3.11.1 | RECRUITER calls saveUser | Login as RECRUITER, call saveUser action | Error: "Admin permissions are required." | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | no user option to create an user
58 | RBAC & Permissions | Permission Enforcement on Server Actions | 3.11.2 | RECRUITER calls grantLeaveAction | Login as RECRUITER, call grantLeaveAction | Error: "Permission denied" | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | recruiter have no option to grant leave
59 | RBAC & Permissions | Permission Enforcement on Server Actions | 3.11.3 | RECRUITER calls createClient | Login as RECRUITER, call createClient | Error: "You do not have permission to modify client records." | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
60 | RBAC & Permissions | Permission Enforcement on Server Actions | 3.11.4 | RECRUITER calls createCandidate | Login as RECRUITER, call createCandidate | Succeeds (has candidates:create) | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
61 | RBAC & Permissions | Permission Enforcement on Server Actions | 3.11.5 | ACCOUNTANT calls createInvoice | Login as ACCOUNTANT, call createInvoice | Succeeds (has billing:full) | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
62 | RBAC & Permissions | Permission Enforcement on Server Actions | 3.11.6 | MANAGER calls updateJobStatus | Login as MANAGER, call updateJobStatus | Succeeds (has jobs:full) | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
63 | RBAC & Permissions | Permission Enforcement on Server Actions | 3.11.7 | TEAM_LEADER calls bulkUpdateCandidateStatus | Login as TL, call bulkUpdateCandidateStatus | Succeeds (has candidates:full) | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | i uploaded valid file but still comes up issue "name is required"
64 | RBAC & Permissions | Permission Enforcement on Server Actions | 3.11.8 | Unauthenticated request | No session, call any server action | Error: permission denied or session error | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
65 | Client Management | Create Client (createClient) | 4.1.1 | Valid client with all fields | Fill all required fields + MSA file upload | Client created, clientCode generated (e.g. TCS00001), MSA record created, audit logged | Critical | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
66 | Client Management | Create Client (createClient) | 4.1.2 | Missing client name | Omit name | Error: "Client name is required" | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
67 | Client Management | Create Client (createClient) | 4.1.3 | Missing primary contact | Omit primaryContactName, Phone, or Email | Error for respective field | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | accepting negative number
68 | Client Management | Create Client (createClient) | 4.1.4 | Missing GST number | Omit gstNumber | Error: "GST number is required" | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | accepting negative number
69 | Client Management | Create Client (createClient) | 4.1.5 | Missing PAN number | Omit panNumber | Error: "PAN number is required" | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
70 | Client Management | Create Client (createClient) | 4.1.6 | Missing address | Omit address | Error: "Address is required" | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
71 | Client Management | Create Client (createClient) | 4.1.7 | No industries selected | Submit empty industries array | Error: "Select at least one industry" | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
72 | Client Management | Create Client (createClient) | 4.1.8 | Missing MSA dates | Omit msaStart or msaEnd | Error: "MSA dates are required" | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
73 | Client Management | Create Client (createClient) | 4.1.9 | Client without MSA file | Submit without file (only dates) | Client created without ClientMSA record, client still has msaStartDate/msaEndDate | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
74 | Client Management | Create Client (createClient) | 4.1.10 | Optional secondary contact | Fill only primary contact fields | Client created with null secondary fields | Low | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
75 | Client Management | Create Client (createClient) | 4.1.11 | Client code uniqueness | Create two clients with same name prefix | Both get unique codes (TCS00001, TCS00002) | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
76 | Client Management | Toggle Client Status (toggleClientStatus) | 4.2.1 | Deactivate client | toggleClientStatus(id, "INACTIVE") | Status changed, audit logged with before/after | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
77 | Client Management | Toggle Client Status (toggleClientStatus) | 4.2.2 | Reactivate client | toggleClientStatus(id, "ACTIVE") | Status changed back | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
78 | Client Management | Toggle Client Status (toggleClientStatus) | 4.2.3 | Invalid client ID | Pass non-existent ID | Prisma error (record not found) | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
79 | Client Management | MSA Reminder Digest (sendMsaReminderDigest) | 4.3.1 | Clients within 60-day window | Create client with MSA ending in < 60 days, run digest | Email sent with summary | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | The email is clickable, but I'm unable to verify if the email was sent
80 | Client Management | MSA Reminder Digest (sendMsaReminderDigest) | 4.3.2 | No clients in window | All MSAs > 60 days out | "No clients are within the 60-day MSA window." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
81 | Job Requirements | Create Job (createJobRequirement) | 5.1.1 | Admin creates open job | Login as ADMIN, fill all fields, status=OPEN | Job created with status=OPEN | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
82 | Job Requirements | Create Job (createJobRequirement) | 5.1.2 | Non-admin creates job | Login as MANAGER, create job with status=OPEN | Job created with status=PENDING_APPROVAL (forced) | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
83 | Job Requirements | Create Job (createJobRequirement) | 5.1.3 | Missing client | Omit client | Error: "Client is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please select an item in the list" this error msg will be generate
84 | Job Requirements | Create Job (createJobRequirement) | 5.1.4 | Missing position title | Omit positionTitle | Error: "Position title is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
85 | Job Requirements | Create Job (createJobRequirement) | 5.1.5 | Zero openings | Set openings=0 | Error: "Openings must be a positive integer." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
86 | Job Requirements | Create Job (createJobRequirement) | 5.1.6 | Negative openings | Set openings=-1 | Error: "Openings must be a positive integer." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
87 | Job Requirements | Create Job (createJobRequirement) | 5.1.7 | Non-integer openings | Set openings=1.5 | Error: "Openings must be a positive integer." | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
88 | Job Requirements | Create Job (createJobRequirement) | 5.1.8 | Missing location | Omit location | Error: "Location is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
89 | Job Requirements | Create Job (createJobRequirement) | 5.1.9 | Experience min > max | Set min=10, max=5 | Error: "Experience min cannot exceed max." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
90 | Job Requirements | Create Job (createJobRequirement) | 5.1.10 | Negative experience | Set min=-1 | Error: "Experience range must be numeric." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
91 | Job Requirements | Create Job (createJobRequirement) | 5.1.11 | Assign recruiters on create | Pass recruiterIds array | JobAssignment records created | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
92 | Job Requirements | Create Job (createJobRequirement) | 5.1.12 | Job code generation | Create job for client TCS | jobCode like TCS0001, unique | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the client is not being created.
93 | Job Requirements | Create Job (createJobRequirement) | 5.1.13 | Non-existent client | Pass fake clientId | Error: "Client not found." | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | I couldn't check it because the job is not being created.
94 | Job Requirements | Job Status Transitions | 5.2.1 | Admin approves pending job | approveJob(jobId) as ADMIN | Status → OPEN | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the job is not being created.
95 | Job Requirements | Job Status Transitions | 5.2.2 | Non-admin tries to approve | approveJob(jobId) as MANAGER | Error: "Only admins can approve jobs." | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the job is not being created.
96 | Job Requirements | Job Status Transitions | 5.2.3 | Approve already-open job | approveJob(jobId) where status=OPEN | Error: "Only pending or on-hold jobs can be approved." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the job is not being created.
97 | Job Requirements | Job Status Transitions | 5.2.4 | Submit for approval | submitJobForApproval(jobId) | Status → PENDING_APPROVAL | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the job is not being created.
98 | Job Requirements | Job Status Transitions | 5.2.5 | Submit already-open job | submitJobForApproval(jobId) where status=OPEN | Error: "Job is already open." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the job is not being created.
99 | Job Requirements | Job Status Transitions | 5.2.6 | Submit already-pending job | submitJobForApproval(jobId) where status=PENDING_APPROVAL | Error: "Job is already awaiting approval." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the job is not being created.
100 | Job Requirements | Job Status Transitions | 5.2.7 | Non-admin sets status to OPEN | updateJobStatus(id, "OPEN") as MANAGER | Error: "Only admins can approve and open jobs." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the job is not being created.
101 | Job Requirements | Job Status Transitions | 5.2.8 | Non-admin moves pending job | MANAGER changes PENDING_APPROVAL to ON_HOLD | Error: "Only admins can move jobs awaiting approval." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the job is not being created.
102 | Job Requirements | Job Status Transitions | 5.2.9 | Update non-existent job | updateJobStatus("fake", "OPEN") | Error: "Job not found." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the job is not being created.
103 | Job Requirements | Job Status Transitions | 5.2.10 | Invalid status value | updateJobStatus(id, "INVALID") | Error: "Invalid status." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the job is not being created.
104 | Job Requirements | Assign Recruiters (assignRecruiters) | 5.3.1 | Assign multiple recruiters | assignRecruiters(jobId, [r1, r2]) | Old assignments deleted, new ones created | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
105 | Job Requirements | Assign Recruiters (assignRecruiters) | 5.3.2 | Reassign (replace) | Assign [r1], then assign [r2, r3] | Only r2, r3 remain | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
106 | Job Requirements | Assign Recruiters (assignRecruiters) | 5.3.3 | Empty recruiter list | assignRecruiters(jobId, []) | All assignments cleared | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
107 | Candidate Management | Create Candidate (createCandidate) | 6.1.1 | Valid candidate with all fields | Fill fullName, primaryPhone, email, all optional fields | Candidate created, phones created, candidateCode generated (CAND0001) | Critical | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
108 | Candidate Management | Create Candidate (createCandidate) | 6.1.2 | Missing full name | Omit fullName | Error: "Full name is required." | Critical | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
109 | Candidate Management | Create Candidate (createCandidate) | 6.1.3 | Invalid name (numbers) | Set fullName to "John123" | Error from validateCandidateName | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
110 | Candidate Management | Create Candidate (createCandidate) | 6.1.4 | Name auto-formatting | Enter "sHRUTI vAID" | Stored as "Shruti Vaid" (proper case) | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
111 | Candidate Management | Create Candidate (createCandidate) | 6.1.5 | Missing primary phone | Omit primaryPhone | Error: "Primary phone is required." | Critical | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
112 | Candidate Management | Create Candidate (createCandidate) | 6.1.6 | Phone not 10 digits | Enter "12345" | Error: "Primary phone must be a 10-digit number." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
113 | Candidate Management | Create Candidate (createCandidate) | 6.1.7 | Duplicate phone within form | Set primaryPhone = secondaryPhone | Error: "Duplicate phone numbers are not allowed within the same candidate." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
114 | Candidate Management | Create Candidate (createCandidate) | 6.1.8 | Phone already in database | Use phone number that exists for another candidate | Error: "Phone number XXXXXXXXXX already exists in the database." | Critical | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
115 | Candidate Management | Create Candidate (createCandidate) | 6.1.9 | Invalid email format | Enter "not-an-email" | Error from validateEmail | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
116 | Candidate Management | Create Candidate (createCandidate) | 6.1.10 | Valid email | Enter "test@example.com" | Stored as-is | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
117 | Candidate Management | Create Candidate (createCandidate) | 6.1.11 | Optional fields omitted | Only provide name + phone | Candidate created with null optional fields | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
118 | Candidate Management | Create Candidate (createCandidate) | 6.1.12 | Invalid noticePeriod enum | Set to "DAYS_45" | Stored as null (ignored) | Low | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
119 | Candidate Management | Create Candidate (createCandidate) | 6.1.13 | Valid noticePeriod | Set to "DAYS_30" | Stored correctly | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
120 | Candidate Management | Create Candidate (createCandidate) | 6.1.14 | With job assignment | Select client, job, and journey status | CandidateApplication created | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
121 | Candidate Management | Create Candidate (createCandidate) | 6.1.15 | Without job assignment | Skip position assignment section | No CandidateApplication created | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
122 | Candidate Management | Create Candidate (createCandidate) | 6.1.16 | Resume upload | Attach PDF file | resumeUrl and resumeFileKey populated | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
123 | Candidate Management | Create Candidate (createCandidate) | 6.1.17 | Multiple phones (all 4) | Fill all 4 phone fields with unique numbers | 4 CandidatePhone records, sortOrder 0-3 | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
124 | Candidate Management | Create Candidate (createCandidate) | 6.1.18 | Candidate code auto-increment | Create two candidates | Codes are sequential (CAND0001, CAND0002) | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | I couldn't check it because the candidate is not being created.
125 | Candidate Management | Merge Candidate (createCandidate with mergeIntoId) | 6.2.1 | Merge into existing | Set merge Into Id, fill form | Existing candidate updated, new phones added, audit action="merge" | Critical | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | There is no option available to merge.
126 | Candidate Management | Merge Candidate (createCandidate with mergeIntoId) | 6.2.2 | Merge with non-existent target | Set mergeIntoId to fake ID | Error: "Target candidate for merge not found." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | There is no option available to merge.
127 | Candidate Management | Merge Candidate (createCandidate with mergeIntoId) | 6.2.3 | Merge adds new phones | Existing has phone A, form has phone B | Both phones exist after merge | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | There is no option available to merge.
128 | Candidate Management | Merge Candidate (createCandidate with mergeIntoId) | 6.2.4 | Merge skips existing phones | Both existing and form have same phone | No duplicate phone created | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | There is no option available to merge.
129 | Candidate Management | Merge Candidate (createCandidate with mergeIntoId) | 6.2.5 | Merge appends remarks | Existing has remarks, form has remarks | Remarks concatenated with [Merged timestamp] prefix | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | There is no option available to merge.
130 | Candidate Management | Merge Candidate (createCandidate with mergeIntoId) | 6.2.6 | Merge with job assignment | Set mergeIntoId + client/job/status | CandidateApplication created for existing candidate | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | There is no option available to merge.
131 | Candidate Management | Merge Candidate (createCandidate with mergeIntoId) | 6.2.7 | Merge phone conflicts with third candidate | Form phone exists for candidate C (not merge target) | Error: "Phone number exists in the database." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | There is no option available to merge.
132 | Candidate Management | Redeploy Candidate (redeployCandidate) | 6.3.1 | Valid redeploy | Select candidate, new job, status, remarks | Old applications deactivated, new one created, journey event logged | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
133 | Candidate Management | Redeploy Candidate (redeployCandidate) | 6.3.2 | Already active on same job | Redeploy to same job that's already active | Error: "Candidate already has an active application for this job." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
134 | Candidate Management | Redeploy Candidate (redeployCandidate) | 6.3.3 | Non-existent candidate | Fake candidateId | Error: "Candidate not found." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
135 | Candidate Management | Redeploy Candidate (redeployCandidate) | 6.3.4 | Non-existent job | Fake jobId | Error: "Job not found." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
136 | Candidate Management | Redeploy Candidate (redeployCandidate) | 6.3.5 | Remarks appended | Provide remarks | Candidate.remarks updated with timestamp prefix | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
137 | Duplicate Candidate Detection |  | 7.1 | Phone match | Enter phone that exists in DB | Match returned with reason "Phone match: XXXXXXXXXX" | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
138 | Duplicate Candidate Detection |  | 7.2 | Email match (case-insensitive) | Enter "TEST@EXAMPLE.COM" when "test@example.com" exists | Match returned | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
139 | Duplicate Candidate Detection |  | 7.3 | Name match (case-insensitive) | Enter "Shruti Vaid" when "SHRUTI VAID" exists | Match returned | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
140 | Duplicate Candidate Detection |  | 7.4 | Multiple match reasons | Same candidate matches on phone AND email | Both reasons shown | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
141 | Duplicate Candidate Detection |  | 7.5 | No matches | Enter entirely new data | hasDuplicates: false, empty matches array | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
142 | Duplicate Candidate Detection |  | 7.6 | Short name ignored | Enter 2-char name "AB" | Name not searched (< 3 chars) | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
143 | Duplicate Candidate Detection |  | 7.7 | Max 5 results | Database has 10 duplicates | Only 5 returned | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
144 | Duplicate Candidate Detection |  | 7.8 | Blur triggers check | Tab out of phone/email/name field | Duplicate check fires after 600ms debounce | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
145 | Duplicate Candidate Detection |  | 7.9 | Dismiss hides alert | Click X on duplicate alert | Alert hidden, duplicatesDismissed=true, no more checks | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
146 | Duplicate Candidate Detection |  | 7.10 | Merge button sets mergeIntoId | Click "Merge" on a match | Hidden mergeIntoId field set, alert cleared, button text changes to "Merge into Existing" | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
147 | Duplicate Candidate Detection |  | 7.11 | Cancel merge | Click "Cancel merge" banner | mergeIntoId cleared, button reverts to "Create Candidate" | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
148 | Duplicate Candidate Detection |  | 7.12 | Form submit after dismiss | Dismiss duplicates then submit | New candidate created (no merge) | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
149 | Duplicate Candidate Detection |  | 7.13 | Multiple phones checked | Fill primary + secondary phone | Both checked against DB | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
150 | Duplicate Candidate Detection |  | 7.14 | Incomplete phone ignored | Enter 5 digits in phone field, blur | Not included in check (< 10 digits) | Low | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
151 | Bulk Operations | Bulk Import Candidates | 8.1.1 | Valid bulk import | Submit JSON array with 3 valid rows | created=3, errors=[] | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | i uploaded valid file but still comes up issue "name is required"
152 | Bulk Operations | Bulk Import Candidates | 8.1.2 | Empty rows | Submit empty string | Error: "No rows provided" | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | i uploaded valid file but still comes up issue "name is required"
153 | Bulk Operations | Bulk Import Candidates | 8.1.3 | Invalid JSON | Submit malformed JSON | Error: "Invalid rows payload" | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | i uploaded valid file but still comes up issue "name is required"
154 | Bulk Operations | Bulk Import Candidates | 8.1.4 | Row missing name | Row with empty name | Error: "Row N: Name is required" | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | i uploaded valid file but still comes up issue "name is required"
155 | Bulk Operations | Bulk Import Candidates | 8.1.5 | Row missing phone | Row without phone1 or phone2 | Error: "Row N: At least one 10-digit phone is required" | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | i uploaded valid file but still comes up issue "name is required"
156 | Bulk Operations | Bulk Import Candidates | 8.1.6 | Phone not 10 digits | Row with phone1="12345" | Error: "Row N: Phone numbers must be 10 digits" | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | i uploaded valid file but still comes up issue "name is required"
157 | Bulk Operations | Bulk Import Candidates | 8.1.7 | Duplicate phone across rows | Row 1 and Row 2 have same phone | Row 2 fails with unique constraint, Row 1 succeeds | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | i uploaded valid file but still comes up issue "name is required"
158 | Bulk Operations | Bulk Import Candidates | 8.1.8 | Mixed success/failure | 5 rows: 3 valid, 2 invalid | created=3, errors=[2 error messages] | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | i uploaded valid file but still comes up issue "name is required"
159 | Bulk Operations | Bulk Import Candidates | 8.1.9 | Optional fields | Row with only name + phone1 | Created with null email, location, experience | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | i uploaded valid file but still comes up issue "name is required"
160 | Bulk Operations | Bulk Status Update | 8.2.1 | Update 3 applications | Select status + 3 valid app IDs | All 3 updated, journey events created for each | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
161 | Bulk Operations | Bulk Status Update | 8.2.2 | Invalid status | Set status="INVALID" | Error: "Select a valid status." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | There is no option available to valid and invalid.
162 | Bulk Operations | Bulk Status Update | 8.2.3 | Empty selection | No application IDs | Error: "No candidates selected." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
163 | Bulk Operations | Bulk Status Update | 8.2.4 | Some IDs invalid | Mix of valid and non-existent IDs | Valid ones updated, skipped count in message | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
164 | Bulk Operations | Bulk Status Update | 8.2.5 | All IDs invalid | All non-existent IDs | Error: "No valid candidate applications found." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
165 | Bulk Operations | Bulk Status Update | 8.2.6 | Inactive application skipped | Include ID of deactivated application | Skipped (query filters isActive: true) | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the candidate is not being created.
166 | Bulk Operations | Bulk Status Update | 8.2.7 | With remarks | Provide custom remarks | Remarks stored in journey events | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
167 | Bulk Operations | Bulk Status Update | 8.2.8 | Without remarks | Omit remarks | Default: "Bulk status update" | Low | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
168 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.1 | Valid CRM entry | Fill candidateApplicationId, recruiterId, contactStatus=CONTACTABLE, disposition=INTERESTED, remarks | CRM entry created, audit logged | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
169 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.2 | Missing application ID | Omit candidateApplicationId | Error: "Candidate application is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
170 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.3 | Missing recruiter | Omit recruiterId | Error: "Recruiter is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
171 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.4 | Invalid contact status | Set to "MAYBE" | Error: "Invalid value for contact status." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
172 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.5 | Valid CONTACTABLE status | contactStatus=CONTACTABLE | Accepted | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
173 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.6 | Valid NON_CONTACTABLE status | contactStatus=NON_CONTACTABLE | Accepted | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
174 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.7 | Invalid disposition | Set to "UNKNOWN" | Error: "Invalid value for disposition." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
175 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.8 | All 20 dispositions | Test each: WRONG_NUMBER, NUMBER_NOT_REACHABLE, LINE_RINGING, SWITCHED_OFF, CALLBACK, INTERESTED, NOT_INTERESTED, etc. | Each accepted | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
176 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.9 | With sub-disposition | Set disposition + valid subDisposition | Both stored | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
177 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.10 | Invalid sub-disposition | Set subDisposition="INVALID" | Error: "Invalid value for sub-disposition." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
178 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.11 | Missing remarks | Omit remarks | Error: "Remarks is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
179 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.12 | Custom occurredAt | Set specific date/time | Stored as provided | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
180 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.13 | Omit occurredAt | Don't set it | Defaults to current timestamp | Low | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
181 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.14 | Invalid occurredAt | Set to "not-a-date" | Error: "Invalid date supplied for call time." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
182 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.15 | With next follow-up date | Set nextFollowUpDate | Stored correctly | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
183 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.16 | Invalid follow-up date | Set nextFollowUpDate to "not-a-date" | Error: "Invalid date supplied for next follow-up." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
184 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.17 | With call recording | Upload audio file | callRecordingUrl and callRecordingKey populated | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
185 | CRM (Call Dispositions) | Create CRM Entry (createCrmEntry) | 9.1.18 | Without call recording | No file attached | callRecordingUrl/Key remain null | Low | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
186 | Billing & Invoicing | Create Invoice (createInvoice) | 10.1.1 | Valid invoice | Fill applicationId, amount, gstNumberSumi | Invoice created, invoiceNumber generated (INV-2026-001), status=RAISED, raisedAt/By set | Critical | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
187 | Billing & Invoicing | Create Invoice (createInvoice) | 10.1.2 | Missing application ID | Omit applicationId | Error: "Candidate application is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please select an item in the list" this error msg will be generate
188 | Billing & Invoicing | Create Invoice (createInvoice) | 10.1.3 | Missing amount | Omit amount | Error: "Amount is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
189 | Billing & Invoicing | Create Invoice (createInvoice) | 10.1.4 | Zero amount | Set amount=0 | Error: "Amount must be a positive number." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
190 | Billing & Invoicing | Create Invoice (createInvoice) | 10.1.5 | Negative amount | Set amount=-100 | Error: "Amount must be a positive number." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
191 | Billing & Invoicing | Create Invoice (createInvoice) | 10.1.6 | Missing Sumi GST | Omit gstNumberSumi | Error: "Sumi GST number is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
192 | Billing & Invoicing | Create Invoice (createInvoice) | 10.1.7 | Non-existent application | Fake applicationId | Error: "Candidate application not found." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
193 | Billing & Invoicing | Create Invoice (createInvoice) | 10.1.8 | With amountWithGst | Set both amount and amountWithGst | Both stored | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
194 | Billing & Invoicing | Create Invoice (createInvoice) | 10.1.9 | Without client GST | Omit gstNumberClient | Falls back to client.gstNumber | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | its creating invoice
195 | Billing & Invoicing | Create Invoice (createInvoice) | 10.1.10 | Invoice number sequential | Create 3 invoices in same year | INV-2026-001, INV-2026-002, INV-2026-003 | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
196 | Billing & Invoicing | Create Invoice (createInvoice) | 10.1.11 | With billing rule ID | Pass billingRuleId | Linked to rule | Low | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
197 | Billing & Invoicing | Invoice Status Transitions (advanceInvoiceStatus) | 10.2.1 | RAISED → APPROVED | advanceInvoiceStatus(id, "APPROVED") | Status updated, approvedAt/By set | Critical | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
198 | Billing & Invoicing | Invoice Status Transitions (advanceInvoiceStatus) | 10.2.2 | APPROVED → CLEARED | advanceInvoiceStatus(id, "CLEARED") | Status updated, clearedAt/By set | Critical | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
199 | Billing & Invoicing | Invoice Status Transitions (advanceInvoiceStatus) | 10.2.3 | RAISED → CLEARED (skip) | Try to go from RAISED to CLEARED | Error: "Raised invoices can only be approved next." | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
200 | Billing & Invoicing | Invoice Status Transitions (advanceInvoiceStatus) | 10.2.4 | APPROVED → RAISED (revert) | Try to go from APPROVED to RAISED | Error: "Approved invoices can only be cleared next." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
201 | Billing & Invoicing | Invoice Status Transitions (advanceInvoiceStatus) | 10.2.5 | CLEARED → anything | Try any transition from CLEARED | Error: "Cleared invoices cannot transition further." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | The feature is working, but no error message is displayed.
202 | Billing & Invoicing | Invoice Status Transitions (advanceInvoiceStatus) | 10.2.6 | Non-existent invoice | Pass fake invoiceId | Error: "Invoice not found." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | There is no search validation for invalid invoice IDs. When a user searches using a fake or non-existent invoice ID, no error message is displayed.
203 | Billing & Invoicing | Billing Alerts | 10.3.1 | Send digest with alerts | Have pending invoices, call sendBillingAlertsDigest | Email sent with up to 10 alerts | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
204 | Billing & Invoicing | Billing Alerts | 10.3.2 | No pending alerts | All invoices cleared | "No billing lifecycle alerts are pending." | Low | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Pending Notifications option is missing
205 | Billing & Invoicing | Billing Alerts | 10.3.3 | Run automations | Have active rules matching candidates | Notifications created for triggers | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
206 | Billing & Invoicing | Billing Alerts | 10.3.4 | No automation matches | No rules match | "No pending billing automations detected." | Low | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Pending Notifications option is missing
207 | Billing Rules | Create Rule (createBillingRule) | 11.1.1 | JOINING rule | ruleType=JOINING, clientId, jobId | Rule created, isActive=true | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
208 | Billing Rules | Create Rule (createBillingRule) | 11.1.2 | DAYS_COMPLETED rule | ruleType=DAYS_COMPLETED, thresholdDays=90 | Rule created with threshold | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
209 | Billing Rules | Create Rule (createBillingRule) | 11.1.3 | DAYS_COMPLETED without threshold | ruleType=DAYS_COMPLETED, omit thresholdDays | Error: "Threshold days required for this rule type." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
210 | Billing Rules | Create Rule (createBillingRule) | 11.1.4 | MILESTONE rule | ruleType=MILESTONE, milestoneDescription="Interview completed" | Rule created | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
211 | Billing Rules | Create Rule (createBillingRule) | 11.1.5 | Invalid rule type | ruleType="CUSTOM" | Error: "Select a valid rule type." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
212 | Billing Rules | Create Rule (createBillingRule) | 11.1.6 | Negative threshold | thresholdDays=-10 | Error: "Threshold days must be a positive number." | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
213 | Billing Rules | Create Rule (createBillingRule) | 11.1.7 | Zero threshold | thresholdDays=0 | Error: "Threshold days must be a positive number." | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
214 | Billing Rules | Update/Toggle/Delete | 11.2.1 | Update rule | Change ruleType and thresholdDays | Updated in DB, audit logged | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
215 | Billing Rules | Update/Toggle/Delete | 11.2.2 | Update without ruleId | Omit ruleId | Error: "Rule ID required." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | No validation or error message is shown to the user.
216 | Billing Rules | Update/Toggle/Delete | 11.2.3 | Toggle active → inactive | toggleBillingRule(activeRuleId) | isActive flipped, audit logged | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
217 | Billing Rules | Update/Toggle/Delete | 11.2.4 | Toggle inactive → active | toggleBillingRule(inactiveRuleId) | isActive flipped back | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
218 | Billing Rules | Update/Toggle/Delete | 11.2.5 | Toggle non-existent | Fake ruleId | Error: "Rule not found." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
219 | Billing Rules | Update/Toggle/Delete | 11.2.6 | Delete rule | deleteBillingRule(ruleId) | Rule removed from DB, audit logged | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
220 | Billing Rules | Update/Toggle/Delete | 11.2.7 | Delete non-existent | Fake ruleId | Prisma error | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
221 | Payroll | Create Payroll Run (createPayrollRun) | 12.1.1 | Valid run | label, periodStart, periodEnd | PayrollRun created, audit logged | Critical | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
222 | Payroll | Create Payroll Run (createPayrollRun) | 12.1.2 | Missing label | Omit label | Error: "Label is required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
223 | Payroll | Create Payroll Run (createPayrollRun) | 12.1.3 | Missing dates | Omit periodStart or periodEnd | Error: "Period start and end are required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
224 | Payroll | Create Payroll Run (createPayrollRun) | 12.1.4 | Invalid dates | Set periodStart="not-a-date" | Error: "Invalid dates provided." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
225 | Payroll | Create Payroll Run (createPayrollRun) | 12.1.5 | End before start | periodEnd < periodStart | Error: "End date cannot precede start date." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
226 | Payroll | Add Invoice to Run (addInvoiceToRun) | 12.2.1 | Add valid invoice | Pass runId + invoiceId | PayrollItem created, totalAmount recalculated | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
227 | Payroll | Add Invoice to Run (addInvoiceToRun) | 12.2.2 | Missing runId | Omit runId | Error: "Run and invoice are required." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
228 | Payroll | Add Invoice to Run (addInvoiceToRun) | 12.2.3 | Non-existent invoice | Fake invoiceId | Error: "Invoice not found." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
229 | Payroll | Add Invoice to Run (addInvoiceToRun) | 12.2.4 | CLEARED invoice → PAID status | Add a CLEARED invoice | PayrollItem.status=PAID | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
230 | Payroll | Add Invoice to Run (addInvoiceToRun) | 12.2.5 | Non-cleared invoice → READY | Add APPROVED invoice | PayrollItem.status=READY | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Non-cleared invoices are missing from the Add Invoice section. Users are unable to view
231 | Payroll | Update Run Status (updateRunStatus) | 12.3.1 | Mark as READY | updateRunStatus(runId, "READY") | Run + all items status=READY | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
232 | Payroll | Update Run Status (updateRunStatus) | 12.3.2 | Mark as PAID | updateRunStatus(runId, "PAID") | Run + all items status=PAID | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
233 | Payroll | Update Run Status (updateRunStatus) | 12.3.3 | Invalid status | updateRunStatus(runId, "INVALID") | Error: "Invalid status." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
234 | Leave Management | Grant Leave (grantLeaveAction) | 13.1.1 | Grant full-day leave | userId, date, leaveType=CASUAL, halfDay=false | LeaveRecord created, quota usage updated | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
235 | Leave Management | Grant Leave (grantLeaveAction) | 13.1.2 | Grant half-day leave | halfDay=true | LeaveRecord created with halfDay=true, quota uses 0.5 | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
236 | Leave Management | Grant Leave (grantLeaveAction) | 13.1.3 | Missing userId | Omit userId | Error: "User and date are required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
237 | Leave Management | Grant Leave (grantLeaveAction) | 13.1.4 | Missing date | Omit date | Error: "User and date are required." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | not proper msg will be generate "please fill in this filed" this error msg will be generate
238 | Leave Management | Grant Leave (grantLeaveAction) | 13.1.5 | Duplicate leave (same user+date) | Grant leave on date that already has leave | Error: "This user already has leave on that date." | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the grant leave is not being created.
239 | Leave Management | Grant Leave (grantLeaveAction) | 13.1.6 | With reason | Provide reason text | Stored in record | Low | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
240 | Leave Management | Grant Leave (grantLeaveAction) | 13.1.7 | Without reason | Omit reason | Stored as null | Low | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
241 | Leave Management | Approve/Reject/Revoke | 13.2.1 | Approve pending leave | approveLeaveAction with valid ID | Status → APPROVED, quota adjusted | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the grant leave is not being created.
242 | Leave Management | Approve/Reject/Revoke | 13.2.2 | Reject pending leave | rejectLeaveAction with valid ID | Status → REJECTED | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the grant leave is not being created.
243 | Leave Management | Approve/Reject/Revoke | 13.2.3 | Revoke granted leave | revokeLeaveAction with valid ID | Record deleted, quota reverted | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the grant leave is not being created.
244 | Leave Management | Approve/Reject/Revoke | 13.2.4 | Missing leave ID | Omit ID for any action | Error: "Leave ID missing." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the grant leave is not being created.
245 | Leave Management | Approve/Reject/Revoke | 13.2.5 | Non-existent leave ID | Pass fake ID | Prisma error | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | I couldn't check it because the grant leave is not being created.
246 | Leave Management | Employee Leave Request (requestLeaveAction) | 13.3.1 | Request casual leave | date, leaveType=CASUAL | LeaveRecord created with status=PENDING | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
247 | Leave Management | Employee Leave Request (requestLeaveAction) | 13.3.2 | Request sick leave | leaveType=SICK | Created | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
248 | Leave Management | Employee Leave Request (requestLeaveAction) | 13.3.3 | Request half-day | halfDay=true | Created with halfDay flag | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "something went wrong" errror msg displayed
249 | Leave Quotas |  | 14.1 | Update existing quota | userId, year=2026, leaveType=CASUAL, total=30 | Quota updated, audit logged with before/after | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Leave quota is not updating, and the Update button is missing.
250 | Leave Quotas |  | 14.2 | Create new quota | User without quota for that year/type | Quota created with used=0 | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Leave quota is not updating, and the Update button is missing.
251 | Leave Quotas |  | 14.3 | Invalid total (negative) | total=-5 | Error: "Invalid input." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | not wrorking
252 | Leave Quotas |  | 14.4 | Missing userId | Omit userId | Error: "Invalid input." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
253 | Leave Quotas |  | 14.5 | Missing year | Omit year | Error: "Invalid input." (NaN) | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
254 | Leave Quotas |  | 14.6 | Zero total | total=0 | Accepted (employee has 0 days) | Low | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | not working
255 | Web Applications Review | Import Application (importApplicationAction) | 15.1.1 | Import valid application | Pass application ID with status=NEW | Candidate created from WebApplication data, candidateCode generated, status→IMPORTED, importedCandidateId set | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Unable to verify this functionality due to the absence of test data in the web application.
256 | Web Applications Review | Import Application (importApplicationAction) | 15.1.2 | Import with job reference | Application has jobId | CandidateApplication also created | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Unable to verify this functionality due to the absence of test data in the web application.
257 | Web Applications Review | Import Application (importApplicationAction) | 15.1.3 | Import without job | Application has no jobId | Only candidate created, no application | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Unable to verify this functionality due to the absence of test data in the web application.
258 | Web Applications Review | Import Application (importApplicationAction) | 15.1.4 | Import already-imported | Application status=IMPORTED | Error: "Already imported." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Unable to verify this functionality due to the absence of test data in the web application.
259 | Web Applications Review | Import Application (importApplicationAction) | 15.1.5 | Missing application ID | Omit ID | Error: "Application ID missing." | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Unable to verify this functionality due to the absence of test data in the web application.
260 | Web Applications Review | Import Application (importApplicationAction) | 15.1.6 | Non-existent application | Fake ID | Error: "Application not found." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Unable to verify this functionality due to the absence of test data in the web application.
261 | Web Applications Review | Import Application (importApplicationAction) | 15.1.7 | Duplicate phone on import | Application phone already exists for another candidate | Phone creation silently skipped (catch block) | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Unable to verify this functionality due to the absence of test data in the web application.
262 | Web Applications Review | Import Application (importApplicationAction) | 15.1.8 | Audit logged | Import succeeds | Audit record with entityType=WebApplication, action=import | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Unable to verify this functionality due to the absence of test data in the web application.
263 | Web Applications Review | Reject Application | 15.2.1 | Reject valid application | Pass ID | status→REJECTED, reviewedById/At set, audit logged | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Unable to verify this functionality due to the absence of test data in the web application.
264 | Web Applications Review | Reject Application | 15.2.2 | Missing ID | Omit ID | Error: "Application ID missing." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Unable to verify this functionality due to the absence of test data in the web application.
265 | Web Applications Review | Mark Under Review | 15.3.1 | Mark as under review | Pass ID | status→UNDER_REVIEW, reviewedById set | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Unable to verify this functionality due to the absence of test data in the web application.
266 | Web Applications Review | Mark Under Review | 15.3.2 | Missing ID | Omit ID | Error: "Application ID missing." | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | Unable to verify this functionality due to the absence of test data in the web application.
267 | Attendance & Login Logs | Attendance Report (View Only) | 16.1.1 | View monthly report | Go to /settings/attendance-report, select month/year | Table shows daysPresent, daysLate, daysOnLeave, avgWorkingHours per employee | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
268 | Attendance & Login Logs | Attendance Report (View Only) | 16.1.2 | Today's summary | Check dashboard | Shows totalActive, loggedIn, late, onLeave counts | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
269 | Attendance & Login Logs | Login Logs (View Only) | 16.2.1 | View logs | Go to /settings/login-logs | Paginated table with login/logout times, IP, late flag | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
270 | Attendance & Login Logs | Login Logs (View Only) | 16.2.2 | Filter by date | Apply date range filter | Only logs within range shown | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
271 | Attendance & Login Logs | Login Logs (View Only) | 16.2.3 | Filter by role | Select specific role | Only logs for that role | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
272 | API Routes | Admin Backup (/api/admin/backup) | 17.1.1 | Create backup | POST /api/admin/backup | Backup file created | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | "status": "local", "message": "Backup storage not configured. Returning data for manual download.", "generatedAt": "2026-06-05T08:20:51.638Z", "data": { "generatedAt": "2026-06-05T08:20:51.638Z", "clients":
273 | API Routes | Admin Backup (/api/admin/backup) | 17.1.2 | List backups | GET /api/admin/backup?action=list | JSON array of backup entries | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | { "error": "Invalid action" }
274 | API Routes | Admin Backup (/api/admin/backup) | 17.1.3 | Download backup | GET /api/admin/backup?action=download&key=xxx | File download | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
275 | API Routes | Admin Backup (/api/admin/backup) | 17.1.4 | Delete backup | DELETE /api/admin/backup?key=xxx | Backup removed | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
276 | API Routes | Admin Backup (/api/admin/backup) | 17.1.5 | Purge old backups | DELETE /api/admin/backup?purge=true | Old backups removed | Low | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | { "deleted": 0, "errors": [] }
277 | API Routes | Admin Backup (/api/admin/backup) | 17.1.6 | Non-admin access | Call as RECRUITER | 401/403 error | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
278 | API Routes | Export Routes | 17.2.1 | Export audit logs | GET /api/audit/export | CSV download of audit entries | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
279 | API Routes | Export Routes | 17.2.2 | Full database export | GET /api/export/full | JSON snapshot (users:manage required) | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
280 | API Routes | Export Routes | 17.2.3 | Calling report export | GET /api/reports/export?report=calling&format=csv | CSV file | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | Client,Job,Candidate,Contact,Disposition,Recruiter,Timestamp
281 | API Routes | Export Routes | 17.2.4 | Master report export | GET /api/reports/export?report=master&format=xls | XLS file | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
282 | API Routes | Export Routes | 17.2.5 | User roster export | GET /api/reports/export?report=users | CSV of all users | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | { "error": "Unknown report type." }
283 | API Routes | Export Routes | 17.2.6 | Client report export | GET /api/reports/export?report=client | CSV of client performance | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | { "error": "Unknown report type." }
284 | API Routes | Export Routes | 17.2.7 | Performance export | GET /api/performance/export | CSV/XLS performance data | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | 0:{"b":"yO646kGon2eu1REpJhMGZ","f":[[["",{"children":["/_not-found",{"children":["__PAGE__",{},"$undefined","$undefined","$undefined",3]},"$undefined","$undefined","$undefined",3]},"$undefined","$undefined",true,3],null,[null,null],true]],"q":"","i":false,"S":false}
285 | API Routes | Export Routes | 17.2.8 | Invoice PDF | GET /api/invoices/{id}/pdf | PDF file generated | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | 0:{"b":"yO646kGon2eu1REpJhMGZ","f":[[["",{"children":["/_not-found",{"children":["__PAGE__",{},"$undefined","$undefined","$undefined",3]},"$undefined","$undefined","$undefined",3]},"$undefined","$undefined",true,3],null,[null,null],true]],"q":"","i":false,"S":false}
286 | API Routes | Notifications | 17.3.1 | Get notification summary | GET /api/notifications/summary | JSON with notifications + unread count | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
287 | API Routes | Notifications | 17.3.2 | Mark all read | POST /api/notifications/mark-read | All unread → read | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | { "ok": true }
288 | API Routes | Notifications | 17.3.3 | Run automation | POST /api/notifications/run | Notifications generated for matching rules | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | { "msa": 8, "candidate": 0, "jobs": 0, "late": 3, "totalCreated": 11 }
289 | API Routes | Global Search | 17.4.1 | Search candidates | GET /api/search/global?q=Shruti | Matching candidates returned | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | { "results": [ { "type": "candidate", "id": "cmk0p34qt000fwwugp601uf9o", "fullName": "Shruti Vaid", "candidateCode": "CAND001", "primaryEmail": "shruti.vaid@example.com" } ] }
290 | API Routes | Global Search | 17.4.2 | Search clients | GET /api/search/global?q=TCS | Matching clients returned | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | { "results": [] }
291 | API Routes | Global Search | 17.4.3 | Search jobs | GET /api/search/global?q=Developer | Matching jobs returned | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | { "results": [] }
292 | API Routes | Global Search | 17.4.4 | Empty query | GET /api/search/global?q= | Empty or error response | Low | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | { "results": [] }
293 | API Routes | Global Search | 17.4.5 | XSS in query | GET /api/search/global?q=<script>alert(1)</script> | Query sanitized, no XSS | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | { "results": [] }
294 | API Routes | Public APIs | 17.5.1 | List open jobs | GET /api/public/jobs | Only OPEN-status jobs returned | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
295 | API Routes | Public APIs | 17.5.2 | Get job by code | GET /api/public/jobs/TCS0001 | Single job details | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | { "error": "Job not found or no longer open" }
296 | API Routes | Public APIs | 17.5.3 | Non-existent job code | GET /api/public/jobs/FAKE999 | 404 or empty | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress | { "error": "Job not found or no longer open" }
297 | API Routes | Public APIs | 17.5.4 | Submit application | POST /api/public/apply with name, email, phone | WebApplication created with trackingToken | Critical | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
298 | API Routes | Public APIs | 17.5.5 | Rate limit (5/day/email) | Submit 6 applications from same email | 6th is rejected | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
299 | API Routes | Public APIs | 17.5.6 | Duplicate check (30 days) | Same email + same job within 30 days | Rejected as duplicate | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
300 | API Routes | Public APIs | 17.5.7 | Track application | GET /api/public/track?token=xxx | Application status timeline | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
301 | API Routes | Public APIs | 17.5.8 | Invalid tracking token | GET /api/public/track?token=fake | Not found / error | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | { "error": "Token and email are required." }
302 | Security & Edge Cases | Input Validation | 18.1.1 | XSS in candidate name | Enter <script>alert(1)</script> as fullName | Rejected by validateCandidateName (non-alpha chars) | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
303 | Security & Edge Cases | Input Validation | 18.1.2 | SQL injection in search | Enter '; DROP TABLE candidates;-- in search | Query parameterized (Prisma), no injection | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
304 | Security & Edge Cases | Input Validation | 18.1.3 | Oversized file upload | Upload 50MB file as resume | Rejected by file-upload validation | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | not working
305 | Security & Edge Cases | Input Validation | 18.1.4 | Wrong file type | Upload .exe as resume | Rejected (allowed: PDF, DOC, DOCX, RTF) | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
306 | Security & Edge Cases | Input Validation | 18.1.5 | HTML in remarks | Enter HTML tags in remarks | Stored as-is but rendered safely (React escapes) | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
307 | Security & Edge Cases | Input Validation | 18.1.6 | Unicode in candidate name | Enter "Priyā Sharma" | Either accepted or rejected by alpha-only rule | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | not working
308 | Security & Edge Cases | Input Validation | 18.1.7 | Very long input | 10,000-char string in any text field | DB column limit or application limit enforced | Low | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
309 | Security & Edge Cases | Input Validation | 18.1.8 | Negative numbers in numeric fields | Negative CTC, negative experience | Rejected or stored as negative (check each field) | Medium | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
310 | Security & Edge Cases | Concurrent Operations | 18.2.1 | Two users approve same invoice | Both click approve simultaneously | One succeeds, one gets "Approved invoices can only be cleared next." | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
311 | Security & Edge Cases | Concurrent Operations | 18.2.2 | Duplicate candidate creation race | Two forms submit same phone simultaneously | One succeeds, one gets unique constraint error | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
312 | Security & Edge Cases | Concurrent Operations | 18.2.3 | Concurrent payroll item addition | Two users add invoice to same run | Both succeed, totalAmount correctly aggregated (transaction) | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
313 | Security & Edge Cases | Audit Trail | 18.3.1 | Every create is audited | Perform any create action | AuditLog entry with action="create" | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
314 | Security & Edge Cases | Audit Trail | 18.3.2 | Status changes have before/after | Change any status | AuditLog has before and after JSON | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
315 | Security & Edge Cases | Audit Trail | 18.3.3 | Merge action audited | Merge a candidate | AuditLog with action="merge" | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
316 | Security & Edge Cases | Audit Trail | 18.3.4 | Bulk operations audited per item | Bulk update 3 items | 3 separate audit entries | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
317 | Security & Edge Cases | Audit Trail | 18.3.5 | GDPR deletion anonymizes audit | Delete candidate via GDPR endpoint | Candidate data removed, audit entries anonymized | Critical | ☐ | ☐ | ☐ | ☐ | ☐ | Pending
318 | Security & Edge Cases | IP Allowlist & Emergency Bypass | 18.4.1 | Blocked IP gets 403 | Access from non-allowlisted IP | "Access restricted" page with detected IP | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
319 | Security & Edge Cases | IP Allowlist & Emergency Bypass | 18.4.2 | Allowed IP passes | Access from allowlisted range | Normal access | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
320 | Security & Edge Cases | IP Allowlist & Emergency Bypass | 18.4.3 | Emergency bypass with valid key | Append ?_ebk=<secret> | Cookie set, redirect to clean URL | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
321 | Security & Edge Cases | IP Allowlist & Emergency Bypass | 18.4.4 | Emergency bypass with wrong key | Append ?_ebk=wrongsecret | 403 page (no cookie set) | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
322 | Security & Edge Cases | IP Allowlist & Emergency Bypass | 18.4.5 | Bypass cookie works | After bypass, access without param | Cookie validated, access granted | High | ☑ | ☐ | ☐ | ☐ | ☐ | In Progress
323 | Security & Edge Cases | IP Allowlist & Emergency Bypass | 18.4.6 | Bypass cookie expires | Wait beyond EMERGENCY_BYPASS_HOURS | Cookie invalid, 403 returned | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | This checkpoint was not tested
324 | Security & Edge Cases | IP Allowlist & Emergency Bypass | 18.4.7 | Short secret rejected | Set EMERGENCY_BYPASS_SECRET < 32 chars | Bypass feature disabled | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | This checkpoint was not tested
325 | Security & Edge Cases | IP Allowlist & Emergency Bypass | 18.4.8 | Auth routes exempt | Access /login and /api/auth from any IP | Always accessible | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | This checkpoint was not tested
326 | Security & Edge Cases | Rate Limiting | 18.5.1 | Under limit | Send 19 requests in 10 seconds | All succeed | Medium | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | This checkpoint was not tested
327 | Security & Edge Cases | Rate Limiting | 18.5.2 | Over limit | Send 21 requests in 10 seconds | 21st returns 429 "Too many requests" | High | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | This checkpoint was not tested
328 | Security & Edge Cases | Rate Limiting | 18.5.3 | No Redis configured | Remove UPSTASH env vars | Rate limiting disabled, all requests pass | Low | ☐ | ☐ | ☐ | ☐ | ☐ | Pending | This checkpoint was not tested

## Summary
Tester | Completed | Pending | Total Checkpoints | Completion %
Manjali | 138 | 190 | 328 | 42.07%
Aditi | 0 | 328 | 328 | 0%
Siddhi | 8 | 320 | 328 | 2.439%
Chinmay | 0 | 328 | 328 | 0%
Overall complete rows | 0
Overall pending rows | 189
Overall in-progress rows | 139
Source file | ADMIN_TEST_CASES.md
Note | Use the dropdown in each tester column to switch unchecked to checked.